## Sheet2
Month | Programme | Progress A | Month | Programme | Progress B | Month | Programme | Progress C
1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0
2 | 2 | 0.5 | 2 | 2 | 0 | 2 | 2 | 0
3 | 3 | 0.7 | 3 | 3 | 0.1 | 3 | 3 | 0
4 | 4 | 1.2 | 4 | 4 | 0.3 | 4 | 4 | 0
5 | 6 | 2 | 5 | 6 | 0.5 | 5 | 6 | 0
6 | 8 | 3 | 6 | 8 | 1 | 6 | 8 | 0
7 | 10 | 4 | 7 | 10 | 1.8 | 7 | 10 | 0.01
8 | 12 |  | 8 | 12 |  | 8 | 12
9 | 14 |  | 9 | 14 |  | 9 | 14
10 | 16 |  | 10 | 16 |  | 10 | 16
11 | 18 |  | 11 | 18 |  | 11 | 18
12 | 20 |  | 12 | 20 |  | 12 | 20
13 | 22 |  | 13 | 22 |  | 13 | 22
14 | 25 |  | 14 | 25 |  | 14 | 25
15 | 28 |  | 15 | 28 |  | 15 | 28
16 | 32 |  | 16 | 32 |  | 16 | 32
17 | 36 |  | 17 | 36 |  | 17 | 36
18 | 42 |  | 18 | 42 |  | 18 | 42
19 | 48 |  | 19 | 48 |  | 19 | 48
20 | 54 |  | 20 | 54 |  | 20 | 54
21 | 60 |  | 21 | 60 |  | 21 | 60
22 | 65 |  | 22 | 65 |  | 22 | 65
23 | 70 |  | 23 | 70 |  | 23 | 70
24 | 75 |  | 24 | 75 |  | 24 | 75
25 | 80 |  | 25 | 80 |  | 25 | 80
26 | 85 |  | 26 | 85 |  | 26 | 85
27 | 90 |  | 27 | 90 |  | 27 | 90
28 | 95 |  | 28 | 95 |  | 28 | 95
29 | 98 |  | 29 | 98 |  | 29 | 98
30 | 100 |  | 30 | 100 |  | 30 | 100

## Package D
MINISTRY OF HIGHER EDUCATION AND HIGHWAYS ROAD DEVELOPMENT AUTHORITY
CENTRAL EXPRESSWAY PROJECT FROM MEERIGAMA TO KURUNAGALA WITH AMBEPUSSA LINK PROJECT PROGRAMME /PROGRESS SCEDULE
PROJECT PROGRAMME/PROGRESS SCHEDULE
NO | PROJECT ACTIVITIES | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PACKAGE D
1 | Construction of Pilot Road(8.50km) | 2017 5: 0.8; 2017 6: 1.6; 2017 7: 2.4; 2017 8: 3.2; 2017 9: 4; 2017 10: 4.8; 2017 11: 5.6; 2017 12: 6.4; 2018 1: 7.2; 2018 2: 8.5
[6 empty] | 0.2 | 1 | 2.3
3 | Construction of Viaducts(04 Nos. - 0.616 Km) | 2017 12: 0.1; 2018 1: 0.15; 2018 2: 0.2; 2018 3: 0.25; 2018 4: 0.3; 2018 5: 0.35; 2018 6: 0.4; 2018 7: 0.45; 2018 8: 0.5; 2018 9: 0.55; 2018 10: 0.6; 2018 11: 0.61
4 | Construction of Culverts & Other Structures(29Nos.) | [10 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 29
5 | Clearing and Grubbing (7.88km) | [6 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 7.88
6 | Roadway Excavation (7.88km) | [7 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 7.88
7 | Embankment and other Areas of Filling (7.88km) | [8 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 7.88
8 | Sub-base and Base Course (7.88km) | [9 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 7.88
9 | Pavement (8.50km) | [10 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 8.5
10 | Drainage(Approx. 20km)
[13 empty] | 1.1 | 2.2 | 3.3 | 4.4 | 5.5 | 6.6 | 7.7 | 8.8 | 9.9 | 11 | 12.1 | 13.2 | 14.3 | 15.4 | 16.5 | 17.6 | 18.7 | 19.8
11 | Incidentals
[22 empty] | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
#NAME?

## Package C
MINISTRY OF HIGHER EDUCATION AND HIGHWAYS ROAD DEVELOPMENT AUTHORITY
CENTRAL EXPRESSWAY PROJECT FROM MEERIGAMA TO KURUNAGALA WITH AMBEPUSSA LINK PROJECT PROGRAMME /PROGRESS SCEDULE
PROJECT PROGRAMME/PROGRESS SCHEDULE
NO | PROJECT ACTIVITIES | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PACKAGE C
1 | Construction of Pilot Road(10.88 km) | 2017 5: 1; 2017 6: 2; 2017 7: 3; 2017 8: 4; 2017 9: 5; 2017 10: 7; 2017 11: 9; 2017 12: 10.8
1
3 | Construction of Viaducts(05 Nos. - 0.57 Km) | 2018 1: 0.05; 2018 2: 0.1; 2018 3: 0.15; 2018 4: 0.2; 2018 5: 0.25; 2018 6: 0.3; 2018 7: 0.35; 2018 8: 0.4; 2018 9: 0.45; 2018 10: 0.57
4 | Construction of Culverts & Other Structures(48 Nos.) | [10 empty] | 4 | 8 | 12 | 16 | 20 | 24 | 28 | 32 | 36 | 40 | 44 | 48
5 | Clearing and Grubbing (10.31km) | [5 empty] | 0.7 | 1.4 | 2.1 | 2.8 | 3.5 | 4.2 | 4.9 | 5.6 | 6.3 | 7 | 7.7 | 8.4 | 9.1 | 9.8 | 10.3
1.2
6 | Roadway Excavation (10.31 km) | [6 empty] | 0.7 | 1.4 | 2.1 | 2.8 | 3.5 | 4.2 | 4.9 | 5.6 | 6.3 | 7 | 7.7 | 8.4 | 9.1 | 9.8 | 10.3
7 | Embankment and other Areas of Filling (10.31 km) | [7 empty] | 0.7 | 1.4 | 2.1 | 2.8 | 3.5 | 4.2 | 4.9 | 5.6 | 6.3 | 7 | 7.7 | 8.4 | 9.1 | 9.8 | 10.3
8 | Sub-base and Base Course (10.31 km) | [8 empty] | 0.7 | 1.4 | 2.1 | 2.8 | 3.5 | 4.2 | 4.9 | 5.6 | 6.3 | 7 | 7.7 | 8.4 | 9.1 | 9.8 | 10.3
9 | Pavement (10.88 km)
[12 empty] | 0.6 | 1.2 | 1.8 | 2.4 | 3 | 3.6 | 4.2 | 4.8 | 5.4 | 6 | 6.6 | 7.2 | 7.8 | 8.4 | 9 | 9.6 | 10.88
10 | Drainage(Approx. 24 km)
[13 empty] | 1.3 | 2.6 | 3.9 | 5.2 | 6.5 | 7.8 | 9.1 | 10.4 | 11.7 | 13 | 14.3 | 15.6 | 16.9 | 18.2 | 19.5 | 20.8 | 22.1 | 24
11 | Incidentals
[22 empty] | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%

## Package B
MINISTRY OF HIGHER EDUCATION AND HIGHWAYS ROAD DEVELOPMENT AUTHORITY
CENTRAL EXPRESSWAY PROJECT FROM MEERIGAMA TO KURUNAGALA WITH AMBEPUSSA LINK PROJECT PROGRAMME /PROGRESS SCEDULE
PROJECT PROGRAMME/PROGRESS SCHEDULE
[38 empty] | PROGRAMME | NOTE : CUMULATIVE FIGURES ARE SHOWN AT THE END OF EACH MONTH
NO | PROJECT ACTIVITIES | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PACKAGE B
1 | Construction of Pilot Road(10.20km) | [6 empty] | 1 | 3 | 5 | 7 | 9 | 10.2
2.17
2 | Construction of Temporary Bridges(05 Nos.) | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
3 | Construction of Viaducts(10 Nos. - 1.94 Km) | [8 empty] | 0.1 | 0.2 | 0.4 | 0.5 | 0.7 | 0.8 | 1 | 1.1 | 1.2 | 1.4 | 1.5 | 1.6 | 1.7 | 1.8 | 1.9 | 2
4 | Construction of Culverts & Other Structures(48Nos.) | [8 empty] | 1 | 3 | 4 | 6 | 8 | 10 | 12 | 14 | 17 | 19 | 21 | 22 | 23 | 24 | 25 | 26 | 28 | 29
5 | Clearing and Grubbing (10.20 km) | [5 empty] | 0.7 | 1.4 | 2.1 | 2.8 | 3.5 | 4.2 | 4.9 | 5.6 | 6.3 | 7.2 | 7.9 | 8.7 | 9.5 | 10.2
2.3
6 | Roadway Excavation (1.2 km) | [7 empty] | 0.2 | 0.4 | 0.6 | 0.8 | 1 | 1.2
7 | Embankment and other Areas of Filling (8.26 km) | [6 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8.2
0.01
8 | Sub-base and Base Course (8.26 km) | [7 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8.2
9 | Pavement (10.20 km) | [8 empty] | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7.5 | 8.5 | 9 | 9.5 | 10.2
10 | Drainage(Approx. 16 km) | [6 empty] | 2.17 6: 1.3; 2.17 7: 2.6 | 3.9 | 5.2 | 6.5 | 7.8 | 9.1 | 10.4 | 11.7 | 13 | 14.3 | 15.6 | 16.9 | 18.2 | 19.5 | 20.8 | 22.1 | 24
11 | Incidentals | [20 empty] | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%

## Package A
MINISTRY OF HIGHER EDUCATION AND HIGHWAYS ROAD DEVELOPMENT AUTHORITY
CENTRAL EXPRESSWAY PROJECT FROM MEERIGAMA TO KURUNAGALA WITH AMBEPUSSA LINK PROJECT PROGRAMME /PROGRESS SCEDULE
PROJECT PROGRAMME/PROGRESS SCHEDULE
NO | PROJECT ACTIVITIES | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PACKAGE A
1 | Construction of Pilot Road(9.71km) | 2017 6: 1.5; 2017 7: 3; 2017 8: 4.5; 2017 9: 6; 2017 10: 7.5; 2017 11: 9; 2017 12: 9.71
[7 empty] | 2 | 4.2
2 | Construction of Temporary Bridges(04 Nos.) | 2017 5: 1; 2017 6: 2; 2017 8: 3; 2017 10: 4
[6 empty] | 1 |  | 2
3 | Construction of Viaducts(09 Nos. - 3.19 Km) | 2017 9: 0.1; 2017 10: 0.2; 2017 11: 0.35; 2017 12: 0.5; 2018 1: 0.65; 2018 2: 0.8; 2018 3: 0.95; 2018 4: 1.1; 2018 5: 1.25; 2018 6: 1.4; 2018 7: 1.6; 2018 8: 1.75; 2018 9: 1.9; 2018 10: 2.1; 2018 11: 2.3; 2018 12: 2.6; 2019 1: 2.9; 2019 2: 3.19
4 | Construction of Culverts & Other Structures(24 Nos.) | 2017 7: 1; 2017 8: 2; 2017 9: 3; 2017 10: 4; 2017 11: 5; 2017 12: 6; 2018 1: 7; 2018 2: 8; 2018 3: 9; 2018 4: 10; 2018 5: 12; 2018 6: 14; 2018 7: 16; 2018 8: 18; 2018 9: 20; 2018 10: 22; 2018 11: 24
0.3
5 | Clearing and Grubbing (9.71 km) | 2017 6: 0.6; 2017 7: 1.2; 2017 8: 1.8; 2017 9: 2.5; 2017 10: 3.3; 2017 11: 4; 2017 12: 4.7; 2018 1: 5.3; 2018 2: 5.9; 2018 3: 6.6; 2018 4: 7.2; 2018 5: 7.9; 2018 6: 8.6; 2018 7: 9.1; 2018 8: 9.71
0.5
6 | Roadway Excavation (0.16 km) | 2017 6: 0.4; 2017 7: 0.8; 2017 8: 1.2; 2017 9: 1.7; 2017 10: 2.2; 2017 11: 2.6; 2017 12: 3.1; 2018 1: 3.6; 2018 2: 4.1; 2018 3: 4.5; 2018 4: 5; 2018 5: 5.4; 2018 6: 5.9; 2018 7: 6.4; 2018 8: 6.8; 2018 9: 7.2; 2018 10: 7.83
7 | Embankment and other Areas of Filling (6.52 km) | 2017 6: 0.4; 2017 7: 0.8; 2017 8: 1.2; 2017 9: 1.7; 2017 10: 2.2; 2017 11: 2.6; 2017 12: 3.1; 2018 1: 3.6; 2018 2: 4.1; 2018 3: 4.5; 2018 4: 5; 2018 5: 5.4; 2018 6: 5.9; 2018 7: 6.4; 2018 8: 6.8; 2018 9: 7.2; 2018 10: 7.83
0.03
8 | Sub-base and Base Course (6.52 km) | 2017 7: 0.4; 2017 8: 0.8; 2017 9: 1.2; 2017 10: 1.7; 2017 11: 2.2; 2017 12: 2.6; 2018 1: 3.1; 2018 2: 3.6; 2018 3: 4.1; 2018 4: 4.5; 2018 5: 5; 2018 6: 5.4; 2018 7: 5.9; 2018 8: 6.4; 2018 9: 6.8; 2018 10: 7.2; 2018 11: 7.83
9 | Pavement (9.71 km) | 2017 10: 0.5; 2017 11: 1; 2017 12: 1.5; 2018 1: 2; 2018 2: 2.5; 2018 3: 3; 2018 4: 3.5; 2018 5: 4; 2018 6: 4.5; 2018 7: 5; 2018 8: 5.5; 2018 9: 6; 2018 10: 6.5; 2018 11: 7; 2018 12: 7.5; 2019 1: 8; 2019 2: 8.5; 2019 3: 9; 2019 4: 9.71
10 | Drainage(Approx. 15 km) | 2017 12: 1.2; 2018 1: 2.4; 2018 2: 3.6; 2018 3: 4.8; 2018 4: 6; 2018 5: 7.2; 2018 6: 8.4; 2018 7: 9.6; 2018 8: 10.8; 2018 9: 12; 2018 10: 13.2; 2018 11: 14.4; 2018 12: 15.6; 2019 1: 16.8; 2019 2: 18; 2019 3: 19.2; 2019 4: 20.4; 2019 5: 21.6
11 | Incidentals | [20 empty] | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 90% | 100%
``